## UserView Functions
User View Functions
| Menu item | submenu | Implemented | Working | Error message | Action
File (Change to Object) | New |  | N |  |  | delete
| Open |  | Y | Y
| Print |  | N |  |  | Delete
| Grant to |  | Y | Y
| Send to |  | N |  |  | Delete
| Export to |  | N |  |  | Delete
| Delete |  | N |  |  | Delete
| Rename |  | N |  |  | Delete
| Properties |  | Y | N | Error message
| Exit |  | N
Edit (Delete) | Cut |  | N |  |  | Delete
| Copy |  | N |  |  | Delete
| Paste |  | N |  |  | Delete
View | More Tiers |  | N |  |  | Delete
| Fewer Tiers |  | N |  |  | Delete
| Admin View |  | Y | Y
| User View |  | Y | Y
| Refresh |  | Y | Y
Tools | Change Password |  | Y | Y
| Run Command |  | Y | ? |  | delete
| RTF Editor |  | Y | N | Error message | delete
| Admin Tool |  | y | N | Exception | delete
| Word |  | N |  |  | delete
| key stores |  | Y | Y
| configure |  | Y | N | Error message | delete
Right Click Menu | Test connect |  |  |  |  | Delete
| Test Read File |  |  |  |  | Delete
| Test Request permissions |  |  |  |  | Delete
| new |  |  |  |  | Delete
open
| open with TH |  |  |  |  | delete
grant to
| send to |  |  |  |  | delete
| Export to |  |  |  |  | delete
| cut |  |  |  |  | delete
| copy |  |  |  |  | delete
| delete |  |  |  |  | delete
| Rename |  |  |  |  | delete
| Select as startup |  |  |  |  | delete
------Not Implemented | properties |  |  |  | Not yet Implemented

## Admin View Functions
Admin View
| Menu item | submenu | Implemented | Working | Error message | Keep?
File | New |  | N |  |  | delete
| Open |  | Y | Y |  | delete
| Print |  | N |  |  | delete
| Grant to |  | Y | Y |  | delete
| Send to |  | N |  |  | delete
| Export to |  | N |  |  | delete
| Delete |  | N |  |  | delete
| Rename |  | N |  |  | delete
| Properties |  | y
| Exit |  | y | Y
Edit (delete) | Cut |  | N |  |  | delete
| Copy |  | N |  |  | delete
| Paste |  | N |  |  | delete
View | More Tiers |  | N |  |  | delete
| Fewer Tiers |  | N |  |  | delete
| Admin View |  | Y | Y
| User View |  | Y | Y
| Refresh |  | Y | Y
Tools | Change Password |  | Y | Y
| Run Command |  | Y | Y |  | delete
| RTF Editor |  | Y | N | Error message | delete
| Admin Tool |  | y | N | Exception | delete
| Word |  | N |  |  | delete
-------------->add | key stores | Keystors | Y | ?
|  | Set Startups | Y | N | Error message | delete
Right Click Menu | Edit |  | Y | N | Error message | delete
| Add policy class |  | Y | Y
| Add user attribute |  | Y | Y
| Add user |  | Y | Y
| Add object attribute |  | Y | Y
------Not Implemented | Add object |  | N
| Mark Node |  | Y | Y
| Assign Marked Node |  | Y | Y
| Delete assignment |  | Y | Y
| Delete Node |  | Y | Y
| Set permissions on |  | Y | Y

## Admin Tool Functions
Admin Tool
| Menu item | submenu | Implemented | Working | Error message | Keep?
File | Import configuration |  | Y | Y
| Import configuration (in block) |  | Y | ? |  | delete
| Export configuration |  | Y | Y
| Test Export |  | Y | N | Exception | delete
| Migrate to PM object |  | Y | Y
| Exit |  | Y | N
View | Change direction |  | Y | Y
| Users/Attributes |  | Y | Y
| Objects/Attributes |  | Y | Y
| Users/Attributes with capabilities |  | Y | ?
| Objects/Attributes with ACEs |  | Y | ?
| Sessions |  | Y | Y
Operations | Policy classes… |  | Y | Y
| Users… |  | Y | Y
| Attribute sets… |  | Y | Y
delete | SACs… |  | Y | Y
| Denies… |  | Y | Y
| DAC Confinement |  | Y | Y
| Tasks… |  | Y | Y
| Static constraints… |  | Y | Y
| Static constraints for attributes |  | Y | Y
| Event/Response |  | Y | Y
| Object classes… |  | Y | Y
| Objects… |  | Y | Y
| Operation sets… |  | Y | Y
| Hosts… |  | Y | Y
| Run command… |  | Y | Y
| Properties… |  | Y | Y
Tools | Reset |  | Y | Y
| Policy Library ==> | IBAC… | Y | Y
|  | DAC… | Y | Y
|  | MLS… | Y | Y |  |  | k
|  | Confinement for DAC user… | Y | Y
|  | DAC user with confinement… | Y | Y
Right Click Menu | Get Connector |  | Y | ? |  | delete
| Get Ccontainers of |  | Y | ? |  | delete
| Get members of |  | Y | ? |  | delete
| Request perms on node |  | Y | Y
| Request perms on node |  | Y | Y
| Is marked node contained in this? |  | Y | Y
------Not Implemented | Info |  | N
| Edit |  | Y | Y
| Edit email account… |  | Y | Y
| Set permissions on… |  | Y | Y
| View permissions |  | Y | Y
| Add policy class |  | Y | Y
| Add user attribute |  | Y | Y
| Add user attribute |  | Y | Y
| Add object attribute |  | Y | Y
| Add object… |  | Y | Y
| Add operation set… |  | Y | Y
| Mark node |  | Y | Y
| Assign marked node |  | Y | Y
| Delete assignment |  | Y | Y
| Delete node |  | Y | Y
| Delete objects from container |  | Y | Y
| Get member objects |  | Y | N | Too Few arguments
| Get pm views |  | Y | ?

## e-Grant Functions
eGrant
| Menu item | submenu | Implemented | Working | Error message | Keep?
Message | new |  | Y | Y
| forward |  | Y | Y/N | Keeps last instance of forwarded email
| save |  | Y | Y
| save attachment |  | Y | Y
| create many Objects |  | N
| Create Linked Objects |  | N
| Delete |  | Y | Y
| Print |  | Y | Y
| Exit |  | Y | Y
Edit | Copy Ctrl+C |  | N
View | Inbox |  | Y | Y
| Outbox |  | Y | Y
| Check Mail |  | Y | N | Exception - Connection refused
Buttons | Check Mail |  | Y | N | Exception - Connection refused
| Inbox |  | Y | Y
| Outbox |  | Y | Y
| new |  | Y | Y
| reply |  | N
| forward |  | Y | Y
| print |  | Y | Y/N | Prints even if nothing is selected
| delete |  | Y | Y

## Apps
Workflow App
| Menu item | submenu | Implemented | Working | Error message
Bottons | browse |  | Y | Y
Bottons | sign |  | Y | Y
Bottons | submit |  | Y | Y
Bottons | cancel |  | Y | Y
RTF Editor
File | open |  | Y | Y
| save |  | Y | Y
| save as |  | Y | Y
| print |  | Y | Y
Edit | Undo |  | Disabled
| Redo |  | Disabled
| Copy |  | Y | Y
| Paste |  | Y | Y | Correct message comes up not allowing to paste
| Select All |  | Y | Y
Font | Style |  | Y | Y
| Family |  | Y | Y
| Size |  | Y | Y
| Color |  | Y | Y
new | cut

## Go Button
Go Button
| Menu item | submenu | Implemented | Working | Error message | Keep?
Applications | Admin |  | Y | N | Wrong Session ID or User
(Go button) | Open Office |  | Y | N | Could not find Open Office frame | Delete
| PDF Viewer |  | Y | N | Loading contines. Wrks with explorer
| Workflow Old |  | Y | N | Submits does not save correctly
| Med-Rec |  | Y | Y
| MS Office Launcher |  | Y | N | Cant launch - ClassNotFound Exception
| Workflow Editor |  | Y | N | Opens up PDFView
| e-grant |  | Y | Y
| Rich Text Editor |  | Y | Y | Opens up but ArrayOutOfBOundException
| Acct-Rec |  | Y | Y | Opens up but ArrayOutOfBOundException
| Exporter |  | Y | N | Address already in use: JVM_Bind
| Open Office--Power Point |  | N
| Open Office--Excel Worksheet |  | N
| Open Office--Word |  | N
Configuration |  |  |  |  | Nothing shows up in the list
(Go button)
Menu | Manager-->Configure |  | Y | Y
| Manager-->exit |  | Y | Y
| View |  | N | N | Nothing on the list
| Windows |  | Y | Y

## Phase II
Policy Machine defects / enhancements for Phase II
| Task | Effort | Category | Estimate (Man hours) | owner
1 | Email external | High | Email
2 | Work flow enhancement | High | Workflow
3 | Tracking Data enhancements | High | Tracking Data
4 | PDF support | High | PDF
5 | Record management | High | Import Objects
6 | Import objects | High | Import Objects
7 | performance | High | Application Enhancement
8 | Administrative interface | High | Application Enhancement
9 | Obligation Fix | High | Application Enhancement
10 | Improve Look and Feel | High | General
11 | mySQL coding | High | MySQL transition